## Product Backlog
PRODUCT BACKLOG
ID | USER STORY | OWNER | PRIORITY | EFFORT | STATUS | DEFINITION OF DONE | NOTES
1 | As a customer, I want to be able to add items to my cart, so that I can buy what I want. | Product Owner | Critical | 3 | In Progress | Performance Test Run
2 | As a customer, I want to be able to view items in my cart, so that I know what I am buying. | Product Owner | Critical | 5 | In Progress | Usabiity Review
3 | As a customer, I want to be able to remove items from my cart, so that I can get rid of items I do not want to buy. | Product Owner | Critical | 2 | To Do | Performance Test Run
4 | As a customer, I want to be able to view the checkout page, so I can confirm what I am buying. | Product Owner | Critical | 5 | To Do | Usability Review
5 | As a customer, I want to be able pay with my credit card, so that I can pay with my preferred payment method. | Product Owner | Critical | 5 | In Progress | Peformance Test Run and Validation Test for Credit Card. | Difficult to test with real money. Transactions could be saved in a text file to act as a confirmation test.
6 | As a customer, I want to be able to view my name and order ID on the waiting list, so that I can identify my order. | Product Owner | Critical | 3 | To Do | Usability Review
7 | As a customer, I want to be able to view a confirmation page, so I know my payment has been successfully processed. | Product Owner | Critical | 3 | In Progress | Performance Test Run
8 | As a manager, I want to be able to login, so that I can access the manager's index page. | Product Owner | Critical | 3 | Complete | Acceptance Criteria met
9 | As a manager, I want to be able to add new staff members, so that the new staff members can access the staff index page. | Product Owner | Critical | 3 | Complete | Acceptance Criteria met
10 | As a manager, I want to be able to revoke access to previous staff members, so only current staff members are able to access the staff page. | Product Owner | Critical | 2 | Complete | Acceptance Criteria met
11 | As a staff member, I want to be able to login, so that I can access the staff page. | Product Owner | Critical | 5 | Complete | Acceptance Criteria met
12 | As a staff member/barista, I want to be able to view incoming orders, so that I can know what orders to make. | Product Owner | Critical | 2 | Complete | Usability Review
13 | As a customer, I want to be able to view the availability of the products, so that I can know which items I can purchase now. | Product Owner | High | 3 | In Progress | Peer Code Review
14 | As a customer, I want to be able to view my approximate waiting time, so I know how long to wait to pick up my order. | Product Owner | High | 3 | In Progress | Peer Code Review
15 | As a customer, I want to be able to view how many orders are in the line, so that I can expect when to pick up my order. | Product Owner | High | 4 | To Do | Peer Code Review
16 | As a customer, I want to be able to choose the cup size of my coffee so that I can get my preferred size of coffee. | Product Owner | High | 1 | Complete | Usability Review
17 | As a staff member/barista, I want to be able to indicate 'ready to pick up', so customers can be informed that when their order is finish making. | Product Owner | High | 3 | Complete | Acceptance Criteria met
18 | As a staff member, I want to be able to change the status of a product, so that customers do not purchase an item that is unavailable. | Product Owner | High | 3 | In Progress | Peer Code Review
19 | As a customer, I want to be able to view the details of my order in the confirmation page, so that I can confirm what I ordered. | Product Owner | Medium | 2 | To Do | Usability Review
20 | As a customer, I want to be able to make changes to the items in my cart, so that I do not need to remove and read items. | Product Owner | Medium | 5 | To Do | Usability Review
21 | As a staff member, I want to be able to remove orders that are picked up on the list, so that I can serve another order. | Product Owner | Medium | 2 | Complete | Performance Test Run
22 | As a customer, I want to be able to view the remaining stock of the product, so that I know how many I can buy. | Product Owner | Low | 4 | To Do | Peer Code Review
23 | As a customer, I want to be able to view the product information, so that I know more about the items I am buying. | Product Owner | Low | 1 | To Do | Usability Review
24 | As a customer, I want to be able to choose product categories, so that I can look for my desired items quickly. | Product Owner | Low | 1 | To Do | Usability Review
25 | As a customer, I want to be able to have a secret keyword provided, so I can prove my identity when I pick up my order. | Product Owner | Low | 1 | To Do | Usability Review | Choose list of random words for keyword?
26 | As a staff member, I want to be able to modify the quantity of the stock, so that customers do not accidentally order too many that are not in stock. | Product Owner | Low | 4 | To Do | Peer Code Review
27 | As a customer, I want to view the menu online, so I know what to order. | Product Owner | High | 3 | Complete | Usablity Review
28 | As a staff member, I want to logout, so that unauthorised users do not access my account. | Product Owner | Medium | 1 | Complete | Performance Test Run
29 | Web Interface | Scrum Team | High | 4 | Complete | Compatability with Laptops, Tablets and Smartphones
30 | Casscade Style Sheet | Scrum Team | Medium | 1 | Complete | Non-Functional Requirements met
31 | Security | Scrum Team | Medium | 3 | Complete | Non-Functional Requirements met
32
33
34
35

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | As a customer, I want to be able to add items to my cart, so that I can buy what I want. | #N/A | #N/A | #N/A | #N/A | #N/A
2 | As a customer, I want to be able to view items in my cart, so that I know what I am buying. | #N/A | #N/A | #N/A | #N/A | #N/A
3 | As a customer, I want to be able to remove items from my cart, so that I can get rid of items I do not want to buy. | #N/A | #N/A | #N/A | #N/A | #N/A
4 | As a customer, I want to be able to view the checkout page, so I can confirm what I am buying. | #N/A | #N/A | #N/A | #N/A | #N/A
5 | As a customer, I want to be able pay with my credit card, so that I can pay with my preferred payment method. | #N/A | #N/A | #N/A | #N/A | #N/A
6 | As a customer, I want to be able to view the availability of the products, so that I can know which items I can purchase now. | #N/A | #N/A | #N/A | #N/A | #N/A
7 | As a customer, I want to be able to view the remaining stock of the product, so that I know how many I can buy. | #N/A | #N/A | #N/A | #N/A | #N/A
8 | As a customer, I want to be able to view the product information, so that I know more about the items I am buying. | #N/A | #N/A | #N/A | #N/A | #N/A
9 | As a customer, I want to be able to choose the cup size of my coffee so that I can get my preferred size of coffee. | #N/A | #N/A | #N/A | #N/A | #N/A
10 | As a customer, I want to be able to choose product categories, so that I can look for my desired items quickly. | #N/A | #N/A | #N/A | #N/A | #N/A
11 | As a customer, I want to be able to view my approximate waiting time, so I know how long to wait to pick up my order. | #N/A | #N/A | #N/A | #N/A | #N/A
12 | As a customer, I want to be able to view how many orders are in the line, so that I can expect when to pick up my order. | #N/A | #N/A | #N/A | #N/A | #N/A
13 | As a customer, I want to be able to view my name and order ID on the waiting list, so that I can identify my order. | #N/A | #N/A | #N/A | #N/A | #N/A
14 | As a customer, I want to be able to have a secret keyword provided, so I can prove my identity when I pick up my order. | #N/A | #N/A | #N/A | #N/A | #N/A
15 | As a customer, I want to be able to view a confirmation page, so I know my payment has been successfully processed. | #N/A | #N/A | #N/A | #N/A | #N/A
16 | As a customer, I want to be able to view the details of my order in the confirmation page, so that I can confirm what I ordered. | #N/A | #N/A | #N/A | #N/A | #N/A
17 | As a staff member/barista, I want to be able to view incoming orders, so that I can know what orders to make. | #N/A | #N/A | #N/A | #N/A | #N/A
18 | As a staff member/barista, I want to be able to indicate 'ready to pick up', so customers can be informed that when their order is finish making. | #N/A | #N/A | #N/A | #N/A | #N/A
19 | As a staff member, I want to be able to remove orders that are picked up on the list, so that I can serve another order. | #N/A | #N/A | #N/A | #N/A | #N/A
20 | As a staff member, I want to be able to login, so that I can access the staff page. | #N/A | #N/A | #N/A | #N/A | #N/A
21 | As a staff member, I want to be able to change the status of a product, so that customers do not purchase an item that is unavailable. | #N/A | #N/A | #N/A | #N/A | #N/A
22 | As a staff member, I want to be able to modify the quantity of the stock, so that customers do not accidentally order too many that are not in stock. | #N/A | #N/A | #N/A | #N/A | #N/A
23 | As a manager, I want to be able to login, so that I can access the manager's index page. | #N/A | #N/A | #N/A | #N/A | #N/A
24 | As a manager, I want to be able to add new staff members, so that the new staff members can access the staff index page. | #N/A | #N/A | #N/A | #N/A | #N/A
25 | As a manager, I want to be able to revoke access to previous staff members, so only current staff members are able to access the staff page. | #N/A | #N/A | #N/A | #N/A | #N/A