## Sprint 1
SPRINT 1 - BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | STATUS | NOTES
5 | As a customer, I want to be able pay with my credit card, so that I can pay with my preferred payment method. | 5.1 | Credit Card Form | Yixuan Wang | Incomplete | Cannot run PHP File; may need to work in Sprint 2
|  | 5.1.1 | Fields for Credit Card Number, Expiry Date and CCV | Yixuan Wang | Incomplete | Cannot be tested to check legitimate credit cards
|  | 5.1.2 | Submitting successful form leads to next page | Yixuan Wang | Incomplete
|  | 5.2 | Paypal Option | Yixuan Wang | Incomplete | Need more time to research; next sprints may implement Paypal
|  | 5.2.1 | Install Paypal PHP SDK to set up Paypal payment | Yixuan Wang | Incomplete
|  | 5.3 | Testing | Yixuan Wang | Incomplete
|  | 5.3.1 | Validation - only numbers can be filled in textbox | Yixuan Wang | Incomplete
11 | As a staff member, I want to be able to login, so that I can access the staff index page. | 11.1 | Login Form | Larry Ho | Complete
|  | 11.1.1 | ID and Password textbox | Larry Ho | Complete
|  | 11.1.2 | Submit button to confirm login details | Larry Ho | Complete
|  | 11.2 | Staff role links to their page | Larry Ho | Complete
|  | 11.3 | Testing | Larry Ho | Complete
|  | 11.3.1 | Only staff members can pass login form, unauthorised users go back to login page. | Larry Ho | Complete
27 | As a customer, I want to view the menu online, so I know what to order. | 27.1 | Show the menu items and their details | Jingbin Yin | Complete
|  | 27.1.1 | Item Name, Price and Images for each item | Jingbin Yin | Complete
|  | 27.2 | Each item links to a separate page for the item | Boyu Yuan | Complete
|  | 27.2.1 | List details of Item; name and price, etc | Boyu Yuan | Complete
|  | 27.2.2 | Add to Cart Button | Jingbin Yin, Boyu Yuan | Complete | Not functional; functionality will be worked in the future
24 | As a customer, I want to be able to choose product categories, so that I can look for my desired items quickly. | 24.1 | Items are divided into categories | Boyu Yuan | Complete
|  | 24.1.1 | Hot Drinks | Boyu Yuan | Complete
|  | 24.1.2 | Sandwiches | Boyu Yuan | Complete
|  | 24.1.2 | Cakes | Boyu Yuan | Complete
|  | 24.2 | Link to correct category of items | Boyu Yuan | Complete

## Sprint 2
SPRINT 2 - BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | STATUS | NOTES
2 | As a customer, I want to be able to view items in my cart, so that I know what I am buying. | 2.1 | Create and host database | Larry Ho | Complete
|  | 2.1.1 | Create table for orders | Larry Ho | Complete
|  | 2.2 | Create page for cart | Cheng Long Liew | Complete
|  | 2.2.1 | Create a table for cart items | Cheng Long Liew | Complete
|  | 2.2.2 | List item name, price and quantity for the item in the cart | Cheng Long Liew | Complete
|  | 2.2.3 | For each item in cart, there is one row | Cheng Long Liew | Complete
|  | 2.2.4 | Total Amount for order | Cheng Long Liew | Incomplete
|  | 2.4 | Testing | Cheng Long Liew, Yixuan Wang | Incomplete
|  | 2.4.1 | Adding an item from the menu to cart has the specific item appear in the table | Cheng Long Liew, Yixuan Wang | Incomplete
|  | 2.4.2 | Correct details for the item in cart | Cheng Long Liew, Yixuan Wang | Complete
|  | 2.4.3 | Total Amount is correct depending on prices | Cheng Long Liew, Yixuan Wang | Incomplete
9 | As a manager, I want to be able to add new staff members, so that the new staff members can access the staff index page. | 9.1 | Create and host database | Larry Ho | Complete
|  | 9.1.1 | Create table for staff members | Larry Ho | Complete
|  | 9.2 | Create form to add staff members | Larry Ho | Complete
|  | 9.2.1 | Add fields for name and password | Larry Ho | Complete
|  | 9.2.2 | Submit form securely to database | Larry Ho | Complete
|  | 9.3 | Testing | Larry Ho | Complete
|  | 9.3.1 | Staff Member table shows the record added via form | Larry Ho | Complete
|  | 9.3.2 | Able to login with the staff member ID and password made with the form | Larry Ho | Complete
13 | As a customer, I want to be able to view the availability of the products, so that I can know which items I can purchase now. | 13.1 | Make an if statement that only items with the status 'Available' will only show | Jingbin Yin | Incomplete
|  | 13.2 | Testing | Jingbin Yin | Incomplete
|  | 13.2.1 | Add placeholder data for items to test if items will appear | Jingbin Yin | Incomplete
|  | 13.2.2 | Unavailable items cannot be added to cart | Jingbin Yin | Incomplete
|  | 13.3.3 | Unavailable items will not appear on the menu | Jingbin Yin | Incomplete
16 | As a customer, I want to be able to choose the cup size of my coffee so that I can get my preferred size of coffee. | 16.1 | Add a field to database for coffee size | Larry Ho, Boyu Yuan | Complete
|  | 16.2 | Add radio buttons for sizes in menu page | Boyu Yuan | Complete
12 | As a staff member/barista, I want to be able to view incoming orders, so that I can make those orders. | 12.1 | Create a table for orders | Larry Ho | Complete
|  | 12.2 | Show table on staff member's page | Boyu Yuan | Complete
|  | 12.3 | Testing | Boyu Yuan | Complete
|  | 12.3.1 | Items in database table shows in website table | Boyu Yuan | Complete
|  | 12.3.2 | Items with status 'Complete' no longer show | Boyu Yuan | Complete
1 | As a customer, I want to be able to add items to my cart, so that I can buy what I want. | 1.1 | Append item to cart with the name and price | Cheng Long Liew | Incomplete
|  | 1.2 | Items in cart are temporary held by session | Cheng Long Liew | Incomplete
|  | 1.3 | Session Items are added to cart table | Cheng Long Liew | Incomplete
|  | 1.4 | Testing | Cheng Long Liew | Incomplete
|  | 1.4.1 | Check if item in cart is the same item added | Cheng Long Liew | Incomplete
|  | 1.4.2 | Check for correct details of item in cart table | Cheng Long Liew | Incomplete

## Sprint 3
SPRINT 3 - BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | STATUS | NOTES
7 | As a customer, I want to be able to view a confirmation page, so I know my payment has been successfully processed. | 7.1 | Add content to confirmation page | Yixuan Wang | Incomplete
|  | 7.1.1 | Items ordered in cart | Yixuan Wang | Incomplete
|  | 7.1.2 | Order ID of order paid | Yixuan Wang | Incomplete
|  | 7.1.3 | Estimated Time that order is ready | Yixuan Wang | Incomplete
|  | 7.2 | Confirmation page is accessed from cart | Yixuan Wang | Incomplete
|  | 7.3 | Testing | Cheng Long Liew | Incomplete
|  | 7.3.1 | Correct items in order | Cheng Long Liew | Incomplete
|  | 7.3.2 | Correct Order ID | Cheng Long Liew | Incomplete
17 | As a staff member, I want to be able to indicate 'ready to pick up', so customers can be informed that when their order is finish making. | 17.1 | Add Button to indicate order is ready to pick up | Boyu Yuan | Complete
|  | 17.2 | Completion page for customers to view where only complete order numbers are shown | Boyu Yuan | Complete
|  | 17.3 | Testing | Boyu Yuan | Complete
|  | 17.3.1 | Button function changes the data in database | Boyu Yuan | Complete
|  | 17.3.2 | Only incomplete orders show in order list page | Boyu Yuan | Complete
18 | As a staff member, I want to be able to change the status of a product, so that customers do not purchase an item that is unavailable. | 18.1 | Functionality to change availability | Jingbin Yin | Incomplete
|  | 18.1.1 | Status is an enumeration displaying 'Available' or 'Unavailable' | Jingbin Yin | Incomplete
|  | 18.1.2 | Checkbox or option box to indicate availability | Jingbin Yin | Incomplete
|  | 18.1.3 | Submit form to make changes to database | Jingbin Yin | Incomplete
|  | 18.2 | Reflect change on menu frontend that only available items are shown | Jingbin Yin | Incomplete
|  | 18.3 | Testing | Jingbin Yin | Incomplete
|  | 18.3.1 | Form successfully changes database depending on choice | Jingbin Yin | Incomplete
|  | 18.3.2 | Unavailable items are not shown in menu | Jingbin Yin | Incomplete
10 | As a manager, I want to be able to revoke access to previous staff members, so only current staff members are able to access the staff page. | 10.1 | Functionality to remove staff member | Larry Ho | Complete
|  | 10.1.1 | On the query table, there is a remove button next to each staff record | Larry Ho | Complete
|  | 10.1.2 | Staff is removed from database once button is pressed | Larry Ho | Complete
|  | 10.2 | Testing | Larry Ho | Complete
|  | 10.2.1 | Removed staff is not in query table | Larry Ho | Complete
|  | 10.2.3 | Removed staff cannot login | Larry Ho | Complete
21 | As a staff member, I want to be able to remove orders that are picked up on the list, so that I can serve another order. | 21.1 | Add a button to remove order from table to indicate completion of order | Boyu Yuan | Complete
|  | 21.2 | Change status of order to complete in database | Boyu Yuan | Complete
|  | 21.3 | Testing | Boyu Yuan | Complete
|  | 21.3.1 | Only incomplete orders are shown in the list of orders | Boyu Yuan | Complete
28 | As a staff member, I want to logout, so that unauthorised users do not access my account. | 28.1 | Logout Button | Boyu Yuan | Complete
|  | 28.2 | Remove Session ID and change role to customer once logged out | Boyu Yuan, Larry Ho | Complete
|  | 28.3 | Link to Orders Table is not visible from navigation bar when logged out | Boyu Yuan | Complete
|  | 28.4 | Testing | Boyu Yuan | Complete
|  | 28.4.1 | Orders Table does not appear in navigation bar | Boyu Yuan | Complete

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #NAME? | #NAME?
| Previous Year | #NAME? | #NAME?
| Position | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Key Metrics | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!